## Sheet1
Risk Matrix Based on Risk Factors
S.No | Task | Predecessors | Risk Factors |  | Risk Exposure | Probability Level | Impact | Risk Rating
|  |  | Likelihood | Impact |  |  |  |  | Risk Matrix
1 | 1 |  | 4 | 7 | 28 | Low | Critical | Critical | Impact |  | Very Low | Low | Medium | High | Critical
2 | 2 | 1 | 6 | 8 | 48 | High | Medium | Severe | Probability | Critical | Moderate | Severe | Severe | Critical | Critical
3 | 3 | 1,2 | 7 | 5 | 35 | Medium | High | Severe |  | High | Sustainable | Moderate | Severe | Critical | Critical
4 | 4 | 3 | 9 | 3 | 27 | Low | Low | Sustainable |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical
5 | 5 | 4 | 6 | 2 | 12 | Low | High | Severe |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical
6 | 6 | 5 | 9 | 8 | 72 | Critical | Critical | Critical |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe
7 | 7 | 5,6 | 5 | 3 | 15 | Low | Medium | Moderate
8 | 8 | 7 | 6 | 4 | 24 | Low | Medium | Moderate
Inherent Risk Matrix
[9 empty] | Impact |  | Very Low | Low | Medium | High | Critical
[9 empty] | Probability | Critical |  |  |  |  | 1
| Probability | Impact |  | Probability | Index |  | Impact | Index |  | High |  |  | 1
| Critical | Critical |  | Critical | 60% and above |  | Critical | >30% |  | Medium |  |  |  | 1
| High | High |  | High | 45% - 59% |  | High | 20% - 29% |  | Low |  | 1 | 1 | 1 | 1
| Medium | Medium |  | Medium | 30% - 44% |  | Medium | 10% - 19% |  | Very Low
| Low | Low |  | Low | 11% -29% |  | Low | <10%
| Very Low | Very Low |  | Very Low | <10% |  | Very Low | 0%